## Data
Sprint period | hours left per day history |  | est. Hours | hours left on each task | individual story points | product backlog id | Task id | Task description | Tasks titel | Checked out date | Done date | Checked OUT [yes / no / done] (empty field means no task)
2014-04-28 | 60 |  | 24 | 0 | 50 |  |  | JavaScript send history to AddToLog | Web client javascript send to log |  |  | no | Was down prioritized, more focus on getting ui flow running for cloudmanager and chatwidget
2014-04-29 | 50 |  | 30 | 0 | 100 |  |  | CloudChatClient -- add ChatWidget to customer homepage | CloudChatClient - add ChatWidget to customer homepage |  |  | done
2014-04-30 | 41 |  | 6 | 0 | 80 |  |  | Setup start stop scanvaserver -- scanvaserver apache start stop -- using /etc/init.d/scanvaserver og stopscanvaserver | scanvaserver apache start stop |  |  | done
2014-05-01 | 40 |  | 3 | 0 | 10 |  |  | Makefile for ubuntu/cygwin testing cloudmanager_context | cloudmanager context make file |  |  | done
2014-05-02 | 34 |  | 4 | 0 | 5 |  |  | Meeting with Copenhagen "kommune" | Kbh meeting Stig Sørensen |  |  | done
2014-05-03 | 30
2014-05-04 | 30
2014-05-05 | 30
2014-05-06 | 20
2014-05-07 | 10
2014-05-08 | 6
2014-05-09 | 4
2014-05-10 | 2
2014-05-11 | 0
hours left : | 0
story points: | 245
velocity p/h | 4.0833
points/day | 24.5
SPRINT GOAL | Profile LOG /customer homepage chat client widget
SPRINT PERIOD | w18-w19 2014
client chat history will be stored in profile area -- communication with customer homepage will work
IMPEDIMENT |  | serverity on progress
|  | Overflow of hours in sprint | 7
|  | hours in sprint | 67
|  |  | hours left : | 0
|  | Story points in sprint |  |  | 245
Note on G2: cavdarserup: 1.4 - As a 'User' I need 'to be able to connect and exchange data between Client Application's and the Server Application' so that 'all users can utilize the server functions/services from a/any modern browser enabled mobile device'. 1.6 - As a 'User' I need 'a Server Database' so that 'i can manage and maintain data related to multiple customer relationships'

## BurnDownChart
NOT CHECKED OUT | CHECKED OUT | HOURS LEFT | DONE | SPRINT GOAL: | Profile LOG /customer homepage chat client widget
w18-w19 2014
Johnny Serup
Web client javascript send to log
CloudChatClient - add ChatWidget to customer homepage
scanvaserver apache start stop
cloudmanager context make file
Kbh meeting Stig Sørensen
|  |  |  | UNPLANNED ITEMS |  | NEXT
velocity = story points per hour
|  |  |  | START DAY | 2014-04-28
|  |  |  | EST. END DAY | 2014-05-11
ACT. END DAY
0
{t} Transfer to next sprint
[T] Transfered from previous sprint

## standup comments
Column1 | What did I do yesterday | What do I plan on doing today | Is there any impediments for todays work
2014-04-28
2014-04-29
2014-04-30
2014-05-01
2014-05-02
2014-05-03
2014-05-04
2014-05-05
2014-05-06
2014-05-07
2014-05-08
2014-05-09
2014-05-10
2014-05-11
This sprint will consist of a subset of tasks which will solve a part of the overall userstory
The goal of this sprint is to go towards being able to create data in a flat file, to create customer data in the database, where database is a flat file
The overal userstory which is a customer asking for the functionality of creating a customer in the database, will be divided into subtasks and these subtasks will be committed to various sprints
The customer is in fact a "virtual customer" it is the systemanalysis and systemspec dokument which yields demands, thus creating user stories, which then in turn ends up as tasks
It is important to note that the virtual customer has his own meetings -- when we consult and reevaluate the systemanalysis and specs -- this yields new demands, fx a DFD function is a demand for a certain feature and this could be translated into a user story, however the demand could be too big for one sprint, so it will have to be dived into tasks, which then in turn could be spread across various sprints --- NOT various developers -- when a user story is committed, then it is committed to one person and that person can make tasks which he/she could recommit to various sprints